Stakeholder Register

Anyone impacted or able to impact the project or its outcome.  They may be internal or external, minor or major.  The object is to identify and understand potential impact.

| Stakeholder | Stakeholder Requirements | Stakeholder Criteria | Assessment of Impact | Strategies for Gaining Support or Reducing Obstacles |
| --- | --- | --- | --- | --- |
|  | Represents the expectations the stakeholder/s have of the project | Specific measures the stakeholder will use when determining if their requirements have been met | Attempt to measure the extent of the impact – simplistically: High, Moderate, Low | Actions that will be taken to manage the stakeholder/s |
| Rushworth Committee of Management | Successful implementation and management of the project | Community taxi service is implemented and running | Moderate | Regular updates through the Project Management Group |
| Rushworth Community Members | Community taxi service is running which services communities needs | Reduce resident isolation and improve community participation in regional activities | High | Regular updates and feedback through social media, print media and survey |
| RANCH | Pilot Project for the neighbourhood house sector to inform future community transport development | Community taxi template is developed transferable to other neighbourhood houses | Moderate | Regular updates through the Steering Committee and continued liaison |
| Campaspe Shire Council | Successful implementation and management of the project and continued viability of the service | Fits in with Campaspe Shire Council strategic plan | Low | Keep Council informed of project progress |
| Department of Transport | Successful implementation and management of the project and continued viability of the service | Demonstrate that all aspects of the MOU are met | Low | Regular updates through the Steering Committee and Milestone reports |